## Project Report
Developer Name | Sukanta Kumar Ranasingh
Project | Review |  | Note | This Report should Reach Us by 10.30 AM Every day prior to start the work.
Started on | 16.5.2016 |  |  | The same Excel sheet will come to us during evening as report of the work done bythe Developer.
Delivery Date | Not Defined
Tester Name | Mr. Debasis Mishra
|  | SL No | Date | Proposed Work of the day. | Time Required (in Hours) | Will complete Today?(Yes/No) | Update(Completed/Uncomplete) | Tester Notes(Bug/Bug free) | PM Note(Share/Rework)
|  | 1 | 16.5.2016 | Set up of admin panel for review(With Laravel and AngularJs) | 6-7 hrs | Yes | Completed
|  | 2 | 17.5.2016 | Set up some Admin Menu with My Account pages | 5-6 hrs | Yes | Uncompleted
|  | 3 | 18.5.2016 | Set up some Admin Menu with My Account pages | 5-6 hrs | Yes | Uncompleted
|  | 4 | 19.5.2016 | TourneyGuru Payment Gateway | 7-8 hrs | Yes
|  | 5 | 21.5.2016 | OutBox | 4-5 hrs | Yes | Completed |  | 7 hrs
|  | 6 | 23.5.2016 | Reviews Admin menu setup | 5-6 hrs | Yes | Uncompleted
|  | 7 | 24.5.2016 | Reviews Admin menu setup | 6-7hrs | Yes | Completed
|  | 8 | 25.5.2016 | 1.Bigcommerce R&D on product availability. 2.Reviews Admin menu setup. | 6-7 hrs | Yes | 1.Link for Review in local system: http://192.168.0.114/reviews/backend 2.Bigcommerce R&D completed. | Login : demo@demo.com/ demo
|  | 9 | 26.5.2016 | 1.Review psd study and start client side design accordingly. | 7-8 hrs | No | Uncompleted
|  | 10 | 27.5.2016 | 1.R&D for generating widget and write RESTful API for the project. | 7-8 hrs | No | Found way to write widget and test in our local server.API work is not started yet.
|  | 11 | 30.5.2016 | R&D on widget and RESTful API to be continued. | 7-8 hours | continue | Uncompleted
|  | 12 | 31.5.2016 | 1.R&D on widget and RESTful API to be continued. 2.Calendar Webservice written for outbox mobile App. | 7-8 hours | Yes | Webservice written completed.
|  | 13 | 1.6.2016 | 1.RESTful API to be continued(review). 2.Outbox webservice will be changed if required. | 7-8 hours | continue | Uncompleted
|  | 14 | 2.6.2016 | 1.RESTful API to be continued(review). 2.Outbox webservice will be changed if required. | 7-8 hours | continue | The files of review project uploaded into uk-best test server.
|  | 15 | 3.6.2016 | 1.Work on the review project to set edit profile and other pages. | 7-8 hrs | Yes | Completed Registration and forgot password page.
|  | 16 | 4.6.2016 | 1.Work on review contents page for home page. 2.Outbox webservice modification if required. | 7-8 hrs | Yes | Edit profile page functionality completed but image is under process.
|  | 17 | 6.6.2016 | 1.Work On review edit profile image and other pages. 2.Outbox webserice part for notification in Mobile app. | 7-8 hrs | to be continue | Uncompleted
|  | 18 | 7.6.2016 | 1.Review project work for user section. 2.Outbox webservice for notification in mobile app 3.Jobportal webservice introduction | 7-8 hrs | to be continue | Uncompleted
|  | 19 | 8.6.2016 | 1.Review project work for user section. 2.Outbox webservice for notification in mobile app 3.Jobportal webservice if required. | 7-8 hrs | to be continue | Uncompleted
|  | 20 | 9.6.2016 | 1.Review project work for admin section. 2.Outbox Notification webservice | 7-8 hrs | to be continue | Uncompleted
|  | 21 | 10.6.2016 | 1.Review project work for news and faq section 2.Outbox Notification webservice. | 7-8 hrs | to be continue | Uncompleted
|  | 22 | 13.6.2016 | 1.Rewiews project work on widgets, news and faqs. 2.Outbox webservice. | 7-8 hrs | to be continue | Uncompleted
|  | 23 | 14.6.2016 | 1.Review project work on widgets, newsa and faqs. 2.RT discussion for new requirement. | 7-8 hrs | to be continue | uncompleted RT discussion completed.
|  | 24 | 15.6.2016 | 1.Review project work. 2.Outbox issue fix. 3.RT discussion for new changes. | 7-8 hrs | complete | Outbox Completed
|  | 25 | 16.6.2016 | 1.Review project work. 2.Outbox webservice | 7-8 hrs | complete | Outbox Completed
|  | 26 | 17.6.2016 | 1.RT New changes for Multiple PTR generation. | 7-8 hrs | uncomplete | RT new work started
|  | 27 | 18.6.2016 | 1.RT New changes for Multiple PTR generation. | 7-8 hrs | uncomplete | RT work in progress
|  | 28 | 20.6.2016 | 1.RT New changes for Multiple PTR generation. 2.Review project work. | 7-8 hrs | to be continue | RT work in progress
|  | 29 | 21.6.2016 | 1.RT New changes for Multiple PTR generation. 2.Review project work. | 7-8 hrs | to be continue | RT webservice written for mobile app.
|  | 30 | 22.6.2016 | 1.RT new changes for multiple PTR. 2.RT webservice for mobile app. | 7-8 hrs | to be continue | RT work in progress
|  | 31 | 23.6.2016 | 1.RT new changes for multiple PTR. 2.RT webservice for mobile app. | 7-8 hrs | to be continue | RT work in progress
|  | 32 | 24.6.2016 | 1.RT new changes for multiple PTR. 2.RT webservice for mobile app. | 7-8 hrs | to be continue | RT work in progress
|  | 33 | 27.6.2016 | 1.RT new changes for multiple PTR. 2.RT webservice for mobile app. | 7-8 hrs | to be continue | RT work in progress
|  | 34 | 28.6.2016 | 1.Boxware issue will resolve. 2.RT new changes for multiple driver support. 3.RT webservice for mobile app. | 7-8 hrs | complete | RT work in progress outbox problem detected.
|  | 35 | 29.6.2016 | 1.Boxware issue will resolve. 2.RT new changes for multiple driver support. 3.RT webservice for mobile app. | 7-8 hrs | to be continue | RT work in progress
|  | 36 | 30.6.2016 | 1.RT new changes for multiple driver support. 2.RT webservice Testing.(Mobile App) | 7-8 hrs | complete | RT Webservice testing complete. RT new changes is about to finish but testing left.
|  | 37 | 1.7.2016 | 1.RT new changes for multiple driver support. 2.RT webservice Testing.(Mobile App) | 7-8 hrs | complete | RT New work completed. But testing is left in server.
|  | 38 | 2.7.2016 | 1.RT new changes testing will be done. 2.Review project work start | 7-8 hrs | continue | RT testing completed.
|  | 39 | 4.7.2016 | 1.RT Testing 2.Review project work 3.Bold communication analysis | 8-9 hrs | continue | Review project in progress.
|  | 40 | 5.7.2016 | 1.RT feedback done | 7-8 hrs | continue | under progress
|  | 41 | 7.7.2016 | 1.RT Feeback done 2.Bold communication work to be done. 3.Outbox modification | 8-9 hrs | continue | RT Complete
|  | 42 | 8.7.2016 | 1.RT Feedback done. 2.Bold communication work to be done. 3.Outbox modification | 8-9 hrs | continue | RT completed. Bold communication completed. Outbox not done.
|  | 43 | 11.7.2016 | 1.Outbox work to be done | 7-8 hrs | continue | RT discussion done.
|  | 44 | 12.7.2016 | 1.RT feedback done 2.Out box work done | 7-8 hrs | continue | RT work complted. Outbox work in progress.
|  | 45 | 13.7.2016 | 1.RT Live preparation. 2.Outbox work done | 7-8 hrs | continue | Outbox Completed. RT work in progress.
|  | 46 | 14.7.2016 | 1.RT Live upload to be done. | 7-8 hrs | complete | RT live update completed.
|  | 47 | 15.7.2016 | 1.RT feedback done 2.Out box work done | 7-8 hrs | complete | Out box completed.
|  | 48 | 16.7.2016 | 1.RT booking issue done | 7-8 hrs | complete | Completed but need to test in server.
|  | 49 | 18.7.2016 | 1.RT booking issue test 2.Outbox work done | 7-8 hrs | complete | RT issue completed. But out box not completed.
|  | 50 | 19.7.2016 | 1.Out work will be done. 2.RT SMTP, Session work will be started. | 7-8 hrs | continue | Outbox completed but RT uncomplete.
|  | 51 | 20.7.2016 | 1.RT SMTP, Session work will be started. | 7-8 hrs | continue | under progress
|  | 52 | 21.7.2016 | 1.RT SMTP, Session work will be started. | 7-8 hrs | continue | under progress
|  | 53 | 22.7.2016 | 1.RT SMTP, Session work will be started. | 7-8 hrs | continue | under progress
|  | 54 | 23.7.2016 | 1.RT SMTP, Session work will be started. | 7-8 hrs | continue | Completed but need to test in server.
|  | 55 | 25.7.2016 | 1.RT SMTP, Session work will be started. | 7-8 hrs | complete | Upload today in test server.
|  | 56 | 27.7.2016 | 1.RT SMTP, Session work will be started. | 7-8 hrs | complete | Upload today in live server. Completed and tested in live.
|  | 57 | 29.8.2016 | 1.Learning Laravel continue | 8 hrs | continue
|  | 58 | 30.8.2016 | 1.Learning Laravel continue | 8 hrs | continue
|  | 59 | 06.9.2016 | 1.RT Quiz issue resolve | 7-8 hrs | complete | completed
|  | 60 | 07.9.2016 | 1.RT Filter Search upgrade done | 7-8 hrs | continue | continue
|  | 61 | 08.9.2016 | 1.RT Filter Search upgrade done | 7-8hrs | complete | Completed and Uploaded in live
|  | 62 | 09.9.2016 | RT changes to be done | 6-7 hrs | complete | completed
|  | 63 | 12.9.2016 | Learning Laravel Continue | 8 hrs | continue
|  | 64 | 13.9.2016 | Photel Work will be started | 7-8 hrs | continue
|  | 65 | 14.9.2016 | Photel Work will be continue | 7-8hrs | continue | uncompleted
|  | 66 | 15.9.2016 | Photel Work will be done | 7-8 hrs | continue
|  | 67 | 16.9.2016 | Photel Work will be done | 7-8 hrs | continue
|  | 68 | 17.9.2016 | 1.RT issue will be resolved 2.Photel work will be done | 7-8 hrs | continue | uncompleted.
|  | 69 | 19.9.2016 | 1.Photel work will be done 2.RT new work discussion | 7-8 hrs | continue | uncompleted
|  | 70 | 20.9.2016 | 1.Photel work will be done | 7-8 hrs | complete | complete and uploaded in live
|  | 71 | 21.9.2016 | 1.Rating project discussion | 7-8 hrs | continue | uncomplete
|  | 72 | 22.9.2016 | 1.Outbox issue resolve and webservice written 2.Risktracker work to be started 3.Rating project discussion | 7-8 hrs | continue | Out box completed.
|  | 73 | 23.9.2016 | 1.Outbox webservice for new field added. 2.Risk tracker work started. | 7-8 hrs | continue | Un-complete
|  | 74 | 26.9.2016 | 1.Rating project discussion 2.Outbox web service if required | 7-8 hrs | continue
|  | 75 | 27.9.2016 | 1.Review project understanding. | 7-8 hrs | continue
|  | 76 | 28.9.2016 | 1.Review project transform to laravel 5.2 | 7-8 hrs | continue
|  | 77 | 29.9.2016 | 1.Review project transform to laravel 5.2 | 7-8 hrs | continue | un-complete
|  | 78 | 1.10.2016 | 1.Review project transform to laravel 5.2 | 7-8 hrs | continue | completed both admin and user section .
|  | 79 | 3.10.2016 | 1.Review project transform to laravel 5.2 | 7-8 hrs | continue | completed except product rating and cron.
|  | 80 | 4.10.2016 | 1.Review project transform to laravel 5.2 | 7-8 hrs | complete | completed conversion
|  | 81 | 5.10.2016` | 1.Laravel learning | 7-8 hrs | continue
|  | 82 | 6.10.2016 | 1.Laravel learning | 7-8 hrs | continue
|  | 83 | 7.10.2016 | 1.RT Notification issue 2.Laravel learning | 7-8 hrs | continue
|  | 84 | 14.10.2016 | 1.Outbox new updates to be done | 7-8 hrs | continue | completed
|  | 85 | 15.10.2016 | 1.Laravel learning | 7-8 hrs | continue